## Risk Management Matrix
Risk Management Matrix
NAME | Anton Beck |  |  |  | OBJECTIVE | Minimizing the Project Risk
REF/ID | PRE-MITIGATION |  |  |  | DEPARTMENT / LOCATION | MITIGATIONS / WARNINGS / REMEDIES | POST-MITIGATION |  |  |  | RISK SEVERITY KEY | RISK LIKELIHOOD KEY | RISK LEVEL KEY | ACCEPTABLE TO PROCEED? KEY
| RISK | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL |  |  | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | ACCEPTABLE TO PROCEED?
| Gold plating inflates scope | UNDESIRABLE | PROBABLE | HIGH | ENGINEERS | Everyone should discuss with team and can add something only after a team decision. The team member should be sure that does not affect some other member to work more. | TOLERABLE | POSSIBLE | LOW | YES | ACCEPTABLE | IMPROBABLE | LOW | YES
SCOP | Scope creep inflates scope | TOLERABLE | POSSIBLE | MEDIUM |  | Mace sure that we don’t go out of scope in our favorte parts, also is good to go out of scope if we fulfill the minimal requirements. | TOLERABLE | POSSIBLE | MEDIUM | YES | TOLERABLE | POSSIBLE | MEDIUM | NO
SCOP | Estimates are inaccurate | UNDESIRABLE | PROBABLE | HIGH | MANAGEMENT | Use trusted and good mathematical estimation methods | TOLERABLE | POSSIBLE | MEDIUM | YES | UNDESIRABLE | PROBABLE | HIGH
SCOP | Activities are missing from scope | INTOLERABLE | PROBABLE | HIGH | MANAGEMENT | Discuss with proffeors/Tutors and also check to not forget anytihg unassigned | UNDESIRABLE | IMPROBABLE | MEDIUM | YES | INTOLERABLE |  | EXTREME
COST | Cost forecasts are inaccurate | ACCEPTABLE | IMPROBABLE | LOW | [5 empty] | YES
CHMGM | Change management overload | UNDESIRABLE | POSSIBLE | MEDIUM |  | Discuss and ignore changes if they will complicate the work more than needed | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
CHMGM | Lack of a change management system | TOLERABLE | POSSIBLE | MEDIUM | [5 empty] | YES
CHMGM | Inaccurate change priorities | INTOLERABLE | PROBABLE | EXTREME | MANAGEMENT | Be carful to check Changes before decidint them | TOLERABLE | POSSIBLE | EXTREME | YES
CHMGM | Low quality of change requests | UNDESIRABLE | IMPROBABLE | EXTREME |  |  | TOLERABLE | IMPROBABLE | HIGH | YES
CHMGM | Change request conflicts with requirements | UNDESIRABLE | IMPROBABLE | EXTREME |  |  | TOLERABLE | IMPROBABLE | HIGH | YES
STAK | Stakeholders become disengaged | INTOLERABLE | IMPROBABLE | LOW
STAK | Stakeholders fail to support project | UNDESIRABLE | IMPROBABLE | MEDIUM
STAK | Stakeholder conflict | UNDESIRABLE | POSSIBLE | HIGH | MANAGEMENT | Discuss everything in details with tutors | TOLERABLE | POSSIBLE | MEDIUM | YES
STAK | Process inputs are low quality | INTOLERABLE | IMPROBABLE | EXTREME
COM | Project team misunderstand requirements | INTOLERABLE | PROBABLE | EXTREME | MANAGEMENT | Be sure everyone understand his part and the requerements include Text Use Cases. | UNDESIRABLE | POSSIBLE | MEDIUM | YES
COM | Communication overhead | UNDESIRABLE | POSSIBLE | MEDIUM | MANAGEMENT | Start working as soon as possible. | TOLERABLE | POSSIBLE | MEDIUM | YES
COM | Under communication | UNDESIRABLE | PROBABLE | HIGH | MANAGEMENT | make sure everyone report weekly this will at least be a form of communication. | TOLERABLE | IMPROBABLE | HIGH | YES
COM | Users have inaccurate expectations | UNDESIRABLE | POSSIBLE | EXTREME | MANAGEMENT | Discuss again with proffesor and tutors what we are building. | TOLERABLE | IMPROBABLE | EXTREME | YES
COM | Impacted individuals aren't kept informed | INTOLERABLE | POSSIBLE | EXTREME | MANAGEMENT | Take resposibility to upload and merge the weekly report for tutors to check. | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
R&T | Resource shortfalls | INTOLERABLE | POSSIBLE | HIGH | MANAGEMENT | Before assigning the tasks to every team member ask for their capabilities | UNDESIRABLE | POSSIBLE | HIGH | YES
R&T | Learning curves lead to delays and cost overrun | UNDESIRABLE | PROBABLE | LOW |  | This should go to unprobable after discussing with proffesors. | TOLERABLE | IMPROBABLE | LOW | YES
R&T | Resources are inexperienced | TOLERABLE | PROBABLE | LOW |  | Try to divide the tasks based on team members experience | TOLERABLE | PROBABLE | LOW | YES
R&T | Resource performance issues | UNDESIRABLE | PROBABLE | MEDIUM |  |  | UNDESIRABLE | PROBABLE | MEDIUM | YES
R&T | eam members with negative attitudes towards the project | UNDESIRABLE | POSSIBLE | LOW |  |  | UNDESIRABLE | POSSIBLE | LOW | YES
R&T | Low team motivation | TOLERABLE | POSSIBLE | LOW | [5 empty] | YES
ARCH | Architecture lacks flexibility | UNDESIRABLE | POSSIBLE | MEDIUM |  | Agile and SCRUM development based archiitecture | TOLERABLE | IMPROBABLE | MEDIUM | YES
ARCH | Architecture is not fit for purpose | UNDESIRABLE | POSSIBLE | HIGH |  | choose some architecturial tools that are confirmed for this type of project. | TOLERABLE | IMPROBABLE | HIGH | YES
ARCH | Architecture is infeasible | UNDESIRABLE | POSSIBLE | MEDIUM | MANAGEMENT | Preform estimation methods for our architecture or choose another archiceture | UNDESIRABLE | POSSIBLE | MEDIUM | YES
DES | Design is infeasible | TOLERABLE | IMPROBABLE | HIGH |  |  | TOLERABLE | IMPROBABLE | HIGH | YES
DES | Design lacks flexibility | UNDESIRABLE | POSSIBLE | EXTREME | MANAGEMENT | Make sure the desig is flexible by performing over it estimation methods for flexibility | TOLERABLE | IMPROBABLE | EXTREME | YES
DES | Design is not fit for purpose | INTOLERABLE | IMPROBABLE | EXTREME |  |  | INTOLERABLE | IMPROBABLE | EXTREME | YES
TECH | Technology components aren't fit for purpose | INTOLERABLE | IMPROBABLE | EXTREME | [5 empty] | YES
TECH | Technology components aren't scalable | UNDESIRABLE | POSSIBLE | HIGH | ENGINEERS | Read documentation carefuly before chhsing components, consider team members experince on similar projects | TOLERABLE | POSSIBLE | MEDIUM | YES
TECH | Technology components aren't interoperable | UNDESIRABLE | PROBABLE | EXTREME | ENGINEERS | Again this can be avoided if we read the full information for components | TOLERABLE | POSSIBLE | HIGH | YES
TECH | Technology components aren't compliant with standards and best practices | INTOLERABLE | PROBABLE | EXTREME | ENGINEERS | Be sre componets fullfill the IEEE and other Internatioal Standars | INTOLERABLE | IMPROBABLE | EXTREME | YES
TECH | Technology components have security vulnerabilities | INTOLERABLE | POSSIBLE | EXTREME | ENGINEERS | Update Security Protocols | ACCEPTABLE | POSSIBLE | MEDIUM | YES
TECH | Technology components are over-engineered | ACCEPTABLE | PROBABLE | LOW | [5 empty] | YES
TECH | Technology components lack stability | UNDESIRABLE | POSSIBLE | MEDIUM | ENGINEERS | This can be accepted as a risk if we prepare a good specification of the system. | ACCEPTABLE | POSSIBLE | MEDIUM | YES
TECH | Technology components aren't extensible | INTOLERABLE | IMPROBABLE | HIGH | [5 empty] | YES
TECH | Technology components aren't reliable | UNDESIRABLE | POSSIBLE | LOW | ENGINEERS | Components are verified to be relaible | ACCEPTABLE | POSSIBLE | LOW | YES
TECH | Information security incidents | ACCEPTABLE | PROBABLE | LOW | [5 empty] | YES
TECH | System outages | TOLERABLE | IMPROBABLE | HIGH | [5 empty] | YES
TECH | Legacy components lack documentation | UNDESIRABLE | PROBABLE | HIGH | MANAGEMENT | Trusted seller | ACCEPTABLE | IMPROBABLE | LOW | YES
TECH | Legacy components are out of support | TOLERABLE | IMPROBABLE | LOW | [5 empty] | YES
TECH | Components or products aren't maintainable | ACCEPTABLE | IMPROBABLE | LOW | [5 empty] | YES
TECH | Project management tool problems & issues | TOLERABLE | POSSIBLE | LOW |  | We are a small team that will and can meet every time | ACCEPTABLE | POSSIBLE | LOW | YES
INTG | Failure to integrate with systems | UNDESIRABLE | IMPROBABLE | HIGH | [5 empty] | YES
INTG | Integration testing environments aren't available | TOLERABLE | POSSIBLE | LOW | [5 empty] | YES
INTG | Failure to integrate components | UNDESIRABLE | PROBABLE | HIGH | MANAGEMENT | As a small team we can control compontents one after other te bo sure | ACCEPTABLE | POSSIBLE | HIGH | YES
INTG | Project disrupts operations | UNDESIRABLE | IMPROBABLE | MEDIUM | [5 empty] | YES
REQ | Requirements fail to align with strategy | UNDESIRABLE | POSSIBLE | MEDIUM
REQ | Requirements fail to align with systems | UNDESIRABLE | POSSIBLE | LOW
REQ | Requirements have compliance issues | UNDESIRABLE | IMPROBABLE | LOW | [5 empty] | YES
REQ | Requirements are ambiguous | UNDESIRABLE | PROBABLE | HIGH
REQ | Requirements are low quality | INTOLERABLE | POSSIBLE | HIGH |  | Check requirements before starting the project | UNDESIRABLE | IMPROBABLE | HIGH | YES
REQ | Requirements are incomplete | UNDESIRABLE | POSSIBLE | LOW |  | We can improve requirements during the process | ACCEPTABLE | PROBABLE | LOW | YES
DIS | Decisions are low quality | UNDESIRABLE | PROBABLE | MEDIUM | MANAGEMENT | We are small team and make decisions together | TOLERABLE | PROBABLE | MEDIUM | YES
DIS | Decisions are incomplete | INTOLERABLE | PROBABLE | HIGH | MANAGEMENT | Meetings and clear decisions documented weekly report will also help to minimize this risk | UNDESIRABLE | POSSIBLE | MEDIUM | NO
PROCU | Loss of intellectual property | ACCEPTABLE | IMPROBABLE | LOW | [5 empty] | YES
AUTH | Project team lack authority to complete work | UNDESIRABLE | POSSIBLE | MEDIUM | MANAGEMENT | Team meeting and remove some requirements if it is out of our scope | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
AUTH | Authority is unclear | INTOLERABLE | PROBABLE | EXTREME | MANAGEMENT | Team meeting and discuss and assign roles to everyone | TOLERABLE | IMPROBABLE | EXTREME | YES
PM | Failure to follow methodology | UNDESIRABLE | PROBABLE | HIGH | MANAGEMENT | Present the methotolgy to all team members and check peridicaly if they are following | TOLERABLE | POSSIBLE | MEDIUM | YES
PM | Errors in key project management processes | TOLERABLE | PROBABLE | MEDIUM | MANAGEMENT | Use of scientific and good estimation methods | TOLERABLE | POSSIBLE | MEDIUM | YES
UA | User interface is low quality | UNDESIRABLE | PROBABLE | HIGH | ENGINEERS | We alredy have a user interface, also make sure everything works on the interface | TOLERABLE | IMPROBABLE | HIGH | YES
UA | User interface isn't accessible | INTOLERABLE | POSSIBLE | EXTREME | ENGINEERS | UI will be on Desktop | INTOLERABLE | IMPROBABLE | EXTREME | YES
UA | Project reduces innovation | INTOLERABLE | IMPROBABLE | EXTREME | [5 empty] | YES
UA | Users reject the product | TOLERABLE | IMPROBABLE | LOW | [5 empty] | YES

## KEY - Risk Assessment Matrix
RISK ASSESSMENT MATRIX KEY
| RISK RATING KEY | LOW | MEDIUM | HIGH | EXTREME
|  | 0 – ACCEPTABLE | 1 – ALARP (as low as reasonably practicable) | 2 – GENERALLY UNACCEPTABLE | 3 – INTOLERABLE
|  | –––––––––––––––––– OK TO PROCEED | –––––––––––––––––– TAKE MITIGATION EFFORTS | –––––––––––––––––– SEEK SUPPORT | –––––––––––––––––– PLACE EVENT ON HOLD
S E V E R I T Y
|  | ACCEPTABLE | TOLERABLE | UNDESIRABLE | INTOLERABLE
|  | LITTLE TO NO EFFECT ON EVENT | EFFECTS ARE FELT, BUT NOT CRITICAL TO OUTCOME | SERIOUS IMPACT TO THE COURSE OF ACTION AND OUTCOME | COULD RESULT IN DISASTER
L I K E L I H O O D | IMPROBABLE | LOW | MEDIUM | MEDIUM | HIGH
| RISK IS UNLIKELY TO OCCUR | – 1 – | – 4 – | – 6 – | – 10 –
| POSSIBLE | LOW | MEDIUM | HIGH | EXTREME
| RISK WILL LIKELY OCCUR | – 2 – | – 5 – | – 8 – | – 11 –
| PROBABLE | MEDIUM | HIGH | HIGH | EXTREME
| RISK WILL OCCUR | – 3 – | – 7 – | – 9 – | – 12 –